## Slide 1: MIRG TRAINING SYSTEM PROJECT

## Slide 2: PROJECT PLAN
A future project, which will be led by the Finnish Border Guard, to create model courses of a uniform MIRG Training System in the Baltic Sea region
The project will be funded by the Ministry for Foreign Affairs of Finland (funding will be confirmed by the end of November 2014)
Continuum of the BSMIR Project which stated that there should be joint standard operating procedures (SOPs) and training for the Maritime Incident Response Groups (MIRG) in the region
MIRG groups are an efficient way to handle ship fires. Many Baltic Sea states offer MIRG services but the most of them do not have coherent standard operating procedures in use.
Planned implementation period: December 2014 – December 2016

## Slide 3: PROJECT OBJECTIVES
Gather MIRG related education experiences, teaching material and operating procedures from different Baltic Sea countries
Create common standard operating procedures for MIRG cooperation for the Baltic Sea region, based on the gathered material
Create model courses of "Common MIRG Training
System of the Baltic Sea"
4. Carry out 3 model courses which would be primarly
intended for persons responsible for the development
of MIRG action or education in their own countries
5. Create teaching material which would enable the Baltic
Sea states to carry out MIRG training courses independently
based on the created teaching material

## Slide 4: NEXT STEPS
Confirmation of funding in the end of November 2014
Preparation phase between December 2014 and May 2015
Relevant fire and rescue services (providing MIRG/RITS services) and maritime SAR authorities from the Baltic Sea region will be invited to join the project during the preparation phase
If the project starts and progresses as planned it will apply a Flagship status in the Priority area on Maritime Safety and Security (PA SAFE) in the EU Strategy for Baltic Sea Region
 Application will be presented in the next meeting
Working phase will start in the beginning of June 2015
For more information contact: Cdr Petteri Leppänen, petteri.leppanen@raja.fi